MERIDIAN

Product Backlog

Know what works. Ship it everywhere.

| Version | 1.0 — MVP |
| --- | --- |
| Target Launch | 12 weeks from kick-off |
| Team | Solo developer + Claude/Cursor |
| Story Points | 1 pt ≈ 1 dev-day (solo calibrated) |

# How to Use This Backlog

This backlog is structured for a solo developer working with agentic coding tools (Claude + Cursor). Every epic maps directly to a branch in your GitHub repo. Every user story becomes a GitHub Issue. Story points are calibrated to solo dev-days, not team velocity.

## Priority Definitions

- Must Have — MVP blocker. Ship is held without it.

- These go into your first GitHub Milestone.

- Should Have — Significant value, not a hard blocker.

- Target for Week 8–10 once the core is stable.

- Could Have — Nice polish or secondary features.

- Post-launch or if sprint has capacity.

## Estimation Scale

- 1 pt — Simple component, query, or config change. Half a day or less.

- 2 pts — Moderate task: new page, API integration hook, or data model change. ~1 day.

- 3 pts — Complex feature: full data pipeline, multi-step UI, or external API integration. 2–3 days.

- 5 pts — Large: a full subsystem (e.g., Inngest job pipeline, full analytics module). 4–5 days.

- 8 pts — Epic-scale work requiring decomposition before sprint. Flag for breakdown.

## GitHub Workflow

- One Epic = one GitHub Milestone

- One User Story = one GitHub Issue, labelled with Epic code + priority

- Acceptance Criteria from Notes column go into the Issue body

- Branch naming: feature/E01-auth, feature/E03-youtube-integration, etc.

# Epic Overview

Eight epics cover the full MVP. Epics E01–E05 are the critical path; E06–E08 are launch-readiness and scale.

| Code | Epic | Milestone | Stories | Est. Points |
| --- | --- | --- | --- | --- |
| E01 | Foundation & Auth | Weeks 1–2 | 6 | 14 pts |
| E02 | Platform Integrations | Weeks 2–4 | 8 | 22 pts |
| E03 | Analytics Engine | Weeks 3–5 | 9 | 24 pts |
| E04 | Pattern Intelligence | Weeks 5–6 | 7 | 18 pts |
| E05 | Repurpose Queue | Weeks 6–9 | 10 | 28 pts |
| E06 | Scheduling & Publishing | Weeks 9–10 | 6 | 16 pts |
| E07 | Monetisation & Subscriptions | Weeks 10–11 | 6 | 14 pts |
| E08 | Mobile App (React Native/Expo) | Weeks 11–12 | 5 | 12 pts |

## Milestone Timeline

| Phase | Timeline | Goal | Epics |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1–4 | Foundation: auth, DB schema, YouTube data pipeline live | E01, E02 |
| Phase 2 | Weeks 5–6 | Analytics dashboard live; pattern engine producing insights | E03, E04 |
| Phase 3 | Weeks 7–9 | Repurpose Queue: transcript → derivatives → review UI | E05 |
| Phase 4 | Weeks 10–11 | Scheduling, publishing, Stripe billing — shippable product | E06, E07 |
| Phase 5 | Weeks 11–12 | Mobile app, polish, Expo EAS build, launch prep | E08 |

| E01 EPIC | Foundation & Auth Monorepo setup, Supabase project, authentication, core database schema, and CI/CD pipeline. Everything else builds on this. Milestone: Phase 1 — Weeks 1–2 |
| --- | --- |

### Context

This epic produces the skeleton that every other epic depends on. It should be completed before any feature work begins. The output is a running Next.js + Expo app, connected to Supabase, with Google OAuth working end-to-end.

### Acceptance Criteria (Epic-Level)

- Turborepo monorepo initialised with apps/web, apps/mobile, packages/api, packages/types, packages/inngest

- Supabase project created; all core tables exist with RLS policies enabled

- Google OAuth sign-in works on web and mobile

- Vercel deployment auto-deploys on push to main

- Expo EAS build pipeline configured for development builds

| ID | User Story | Priority | Points | Notes |
| --- | --- | --- | --- | --- |
| E01-01 | As a developer, I want to initialise a Turborepo monorepo with web (Next.js) and mobile (Expo) apps and shared packages so that I have a single source of truth for all code from day one. | Must | 2 | Run: npx create-turbo@latest. Configure tsconfig paths. Shared packages: api, types, ui, inngest. |
| E01-02 | As a developer, I want to provision a Supabase project with the full core database schema (creators, connected_platforms, content_items, performance_snapshots, pattern_insights, repurpose_jobs) so that all data has a home before any integration code is written. | Must | 3 | Enable RLS on all tables. Write migration SQL into /supabase/migrations. Include indexes on creator_id and published_at. |
| E01-03 | As a new user, I want to sign in with my Google account so that I can access Meridian without creating a separate password. | Must | 2 | Supabase Auth with Google provider. On first sign-in, insert row into creators table. Handle token refresh. |
| E01-04 | As a developer, I want to configure row-level security so users can only access their own data so that no user can ever read or write another user's records. | Must | 2 | RLS policy template: auth.uid() = creator_id on all tables. Test with Supabase Studio. |
| E01-05 | As a developer, I want to set up Vercel deployment connected to the GitHub repo so that every push to main deploys automatically with zero manual steps. | Must | 1 | Connect Vercel to monorepo. Set NEXT_PUBLIC_SUPABASE_URL and SUPABASE_SERVICE_ROLE_KEY env vars. |
| E01-06 | As a developer, I want to configure Expo EAS for development and preview builds so that I can test the mobile app on device at any point without manual Xcode setup. | Must | 2 | eas.json with development and preview profiles. EAS build runs in CI via GitHub Actions. |

| E02 EPIC | Platform Integrations OAuth connections and data ingestion for YouTube (primary), Instagram (secondary), and newsletter platforms. Scheduled sync via Inngest. Milestone: Phase 1 — Weeks 2–4 |
| --- | --- |

### Context

Platform integrations are the most technically variable work in the MVP. Build YouTube first and fully — it has the best-documented API, the most permissive access, and is the highest-value platform for the target user. Instagram is second. TikTok is post-MVP due to app review timelines. Beehiiv is third for newsletter data.

### Integration Build Order

- YouTube (YouTube Data API v3 + YouTube Analytics API) — Week 2–3

- Instagram (Meta Graph API) — Week 3–4

- Beehiiv (REST API) — Week 4

- TikTok — Post-MVP (app review required)

| ID | User Story | Priority | Points | Notes |
| --- | --- | --- | --- | --- |
| E02-01 | As a creator, I want to connect my YouTube channel to Meridian via OAuth so that my content and analytics are automatically imported. | Must | 3 | Google OAuth with YouTube scopes: youtube.readonly, yt-analytics.readonly. Store encrypted access + refresh tokens in connected_platforms. |
| E02-02 | As a developer, I want to build an Inngest job that fetches all YouTube video metadata for a connected channel so that content_items are populated on first connect and kept current. | Must | 3 | Fetch via YouTube Data API /videos. Fields: id, title, published_at, duration, thumbnail_url. Paginate with nextPageToken. Upsert into content_items. |
| E02-03 | As a developer, I want to build an Inngest cron job that fetches YouTube Analytics (views, watch time, engagement) for each content item and stores snapshots so that performance data is always fresh without manual action. | Must | 3 | YouTube Analytics API /reports. Capture at 1-day, 7-day, 30-day marks per video. Store in performance_snapshots. Run daily at 3am UTC. |
| E02-04 | As a developer, I want to implement automatic OAuth token refresh for YouTube with silent re-auth UI on failure so that analytics never silently go dark due to expired tokens. | Must | 2 | Check token expiry before each API call. Refresh using refresh_token. If refresh fails, set connected_platforms.status = reauth_required and surface alert in dashboard. |
| E02-05 | As a creator, I want to connect my Instagram account to Meridian so that my Instagram content performance is tracked alongside YouTube. | Should | 3 | Meta Graph API. Requires Business or Creator account. Scopes: instagram_basic, instagram_manage_insights. Fetch media and insights. |
| E02-06 | As a developer, I want to build an Inngest job that fetches Instagram media metadata and engagement metrics so that Instagram content_items and performance_snapshots are populated. | Should | 2 | GET /{media-id}/insights for reach, impressions, engagement. Map to normalised performance_snapshots schema. |
| E02-07 | As a creator, I want to connect my Beehiiv newsletter to Meridian so that my newsletter open rates and clicks are tracked in one place. | Should | 2 | Beehiiv REST API v2. API key auth (no OAuth). Fetch /publications/{id}/posts with stats. Map to content_items with content_type = newsletter. |
| E02-08 | As a creator, I want to see which of my platforms are connected and their sync status on a settings page so that I know immediately if a platform needs re-authentication. | Must | 1 | Settings > Connections page. Show platform icon, connected/disconnected/reauth_required status, last synced time. Connect/disconnect buttons. |

| E03 EPIC | Analytics Engine Cross-platform analytics dashboard: content performance overview, per-post deep-dive, cross-platform comparison, and content lineage view. Milestone: Phase 2 — Weeks 3–5 |
| --- | --- |

### Context

This epic is the "PostMortem" half of Meridian. The analytics engine does not require AI — it is deterministic computation over the performance_snapshots table. The AI (Pattern Intelligence, E04) sits on top of this data. Build the data layer and basic charts first; patterns come in E04.

| ID | User Story | Priority | Points | Notes |
| --- | --- | --- | --- | --- |
| E03-01 | As a creator, I want to see an overview dashboard showing my top-performing content across all platforms in the last 30 days so that I get a single pulse-check on my content health at a glance. | Must | 3 | Metrics: total views, avg engagement rate, best performing piece, worst performing piece. Recharts bar chart. Filter: 7d / 30d / 90d. |
| E03-02 | As a creator, I want to see all my content items in a sortable, filterable table with key metrics so that I can quickly find any piece of content and compare performance. | Must | 2 | Columns: title, platform, published_at, views, engagement_rate, watch_time (video). Sort by any column. Filter by platform and date range. |
| E03-03 | As a creator, I want to click into any content item and see its full performance timeline (1-day, 7-day, 30-day snapshots) as a chart so that I can see how a piece of content decayed or sustained over time. | Must | 2 | Line chart: views and engagement rate over time. Show parent and all derivative children content_items linked below. |
| E03-04 | As a creator, I want to see a cross-platform comparison view showing how my content performs on each platform side-by-side so that I understand where to focus my energy across platforms. | Should | 3 | Normalised engagement rate (platform-adjusted) per platform. Radar chart for multi-metric comparison. Time range selector. |
| E03-05 | As a creator, I want to see a content lineage view that shows me the original piece and all its repurposed derivatives in a tree so that I can measure how much total reach a single piece of content generated across all its versions. | Must | 3 | Tree view using parent_id FK chain. Show total combined reach across all derivatives. Link to deep-dive for each node. |
| E03-06 | As a creator, I want to see a posting consistency heatmap (GitHub-style calendar) showing my publishing activity so that I can spot gaps in consistency that might explain audience growth plateaus. | Should | 2 | Calendar grid: each cell = a day. Colour intensity = pieces published. Click a day to see what was published. |
| E03-07 | As a creator, I want to filter all analytics views by content type (video, short, newsletter, podcast) so that I can analyse each content format independently. | Should | 1 | Multi-select filter chip component. Persisted in URL params so filter state is shareable/bookmarkable. |
| E03-08 | As a creator, I want to export my analytics data as a CSV so that I can use it in my own spreadsheets or share it with a brand partner. | Could | 1 | Export visible data table to CSV. Include all visible columns. Trigger download from browser. |
| E03-09 | As a developer, I want to build a normalisation layer that converts platform-native metrics into a consistent schema so that cross-platform comparisons are apples-to-apples. | Must | 2 | Each platform reports metrics differently. Map to: views (integer), engagement_rate (float 0–1), watch_time_seconds (nullable). Document mapping in code comments. |

| E04 EPIC | Pattern Intelligence Weekly personalized insight engine: statistical pattern computation over performance history, Claude-narrated summaries, and weekly digest email. Milestone: Phase 2 — Weeks 5–6 |
| --- | --- |

### Context

This is the core differentiator of PostMortem versus a standard analytics dashboard. The pattern engine runs on a weekly Inngest cron, computes statistical patterns from the creator's own data (not industry benchmarks), and writes them to pattern_insights. Claude then narrates these patterns in plain language. The weekly digest email is the retention hook.

### Pattern Types (MVP)

- Day-of-week performance — which days consistently outperform your baseline

- Time-since-publish decay — how quickly your content loses momentum vs. your norm

- Content length vs. performance — short vs. long form for your specific audience

- Posting frequency effect — does posting more help or hurt your per-post performance

- Recency spike — do your best pieces share a time-proximity to trending topics

| ID | User Story | Priority | Points | Notes |
| --- | --- | --- | --- | --- |
| E04-01 | As a developer, I want to build a weekly Inngest cron job that computes statistical patterns from each creator's performance_snapshots so that pattern data is always fresh and personalized without manual triggers. | Must | 5 | For each creator with 30+ days of data: compute mean/std by day-of-week, content type, length bucket, posting frequency. Write results to pattern_insights as JSON + confidence score. |
| E04-02 | As a developer, I want to call the Claude API to narrate each computed pattern as clear, actionable plain English so that creators read insights, not statistics. | Must | 3 | System prompt: "You are a creator analytics coach. Given statistical patterns, write 2–3 sentence insight narratives." Strict JSON output format. Include confidence label (Strong / Moderate / Emerging). |
| E04-03 | As a creator, I want to see my personalised pattern insights on my dashboard in a dedicated Insights panel so that I know what my data is telling me every time I open the app. | Must | 2 | Display latest pattern_insights. Each insight card: icon, headline, narrative, confidence badge, data window label. Animate in on first load. |
| E04-04 | As a creator, I want to see which specific pieces of content were used to derive each pattern so that I can verify the insight makes sense and isn't based on outliers. | Should | 2 | Expandable "evidence" section on each insight card. List top 3–5 content_items that contributed most to the pattern. Link to deep-dive. |
| E04-05 | As a developer, I want to build a minimum data threshold check before generating patterns so that creators with fewer than 30 days of data see a clear progress indicator rather than misleading insights. | Must | 1 | If < 30 days data: show "building your baseline" progress bar. Estimate days until first insights based on content frequency. |
| E04-06 | As a creator, I want to receive a weekly digest email every Monday summarising my top patterns and best/worst performing content from the past week so that I get value from Meridian even when I haven't opened the app. | Must | 3 | Resend + React Email. Template: week summary header, top 2 insights, best piece, worst piece, one actionable tip. Inngest cron: Mondays 8am in creator's local timezone. |
| E04-07 | As a creator, I want to dismiss or mark insights as "already knew this" so the system learns my awareness level so that my insight panel stays fresh and doesn't repeat things I've already absorbed. | Could | 1 | Dismiss button on each insight card. Dismissed insights archived, not deleted. Add dismissed_at timestamp to pattern_insights. |

| E05 EPIC | Repurpose Queue The Repurpose Queue half of Meridian: transcript extraction, Claude-powered multi-format content generation, creator review/edit UI, and content lineage tracking. Milestone: Phase 3 — Weeks 6–9 |
| --- | --- |

### Context

This is the "Repurpose Queue" half of Meridian — and the most technically complex epic. The key insight is that repurposing is a workflow, not a one-click feature. Creators approve and edit before anything publishes. The content lineage created here feeds directly back into the analytics engine to close the learn → act → measure loop.

### Supported Output Formats (MVP)

- Twitter/X Thread — 5–8 tweets, hook tweet first, structured for engagement

- LinkedIn Post — 150–300 words, professional register, structured with line breaks

- Newsletter Paragraph — 80–120 words, conversational, teaser format

- Short-form Caption (Instagram/TikTok) — hook + body + CTA + hashtags

- YouTube Shorts Concept — timestamp suggestion + hook script outline

| ID | User Story | Priority | Points | Notes |
| --- | --- | --- | --- | --- |
| E05-01 | As a creator, I want to submit any of my connected content items for repurposing with one click from the analytics dashboard so that the workflow starts from content I'm already thinking about rather than a blank import screen. | Must | 2 | Repurpose button on each content_item card/row. Opens format selection modal. Creates repurpose_jobs row with status=pending. |
| E05-02 | As a developer, I want to build an Inngest job that fetches or extracts the transcript for a submitted video or audio content item so that Claude has text to work from rather than guessing from metadata alone. | Must | 3 | YouTube: fetch captions via YouTube Data API /captions. If no captions: call OpenAI Whisper API on audio stream URL. Store transcript in repurpose_jobs.source_transcript. |
| E05-03 | As a developer, I want to build a Claude API integration that generates derivatives in each selected format from a transcript so that creators get a first draft for every selected format without manual writing. | Must | 5 | System prompt per format (5 format-specific prompts). Return structured JSON: { format, content, platform, char_count }. Max 2000 tokens per format call. Handle rate limits with Inngest retry. |
| E05-04 | As a developer, I want to build pattern-aware prompting that injects the creator's top insights into the repurpose prompt so that the generated content is informed by what has actually worked for that creator, not generic best practices. | Should | 2 | Before calling Claude, fetch creator's latest pattern_insights. Inject top 2 insights into system prompt as context: "This creator's data shows their audience responds best to..." |
| E05-05 | As a creator, I want to review all generated derivatives in a side-by-side queue view before anything is published so that I stay in control of what goes out under my name. | Must | 3 | Queue UI: left panel = source content preview, right panel = tabbed derivative cards per format. Each card: editable text area (inline), char count, platform preview mock. Approve / Edit / Reject per card. |
| E05-06 | As a creator, I want to edit any generated derivative inline before approving it so that I can fix tone, add personal context, or adjust for platform nuances without leaving the app. | Must | 2 | Contenteditable or textarea per derivative card. Auto-save draft edits to repurpose_jobs.derivatives JSONB column. Char count updates live. Warn if over platform limit. |
| E05-07 | As a creator, I want to see a content lineage map that connects approved derivatives back to the source content item so that I can track the total reach generated by one original piece across all its repurposed forms. | Must | 2 | On approval, write approved derivative as a new content_item with parent_id pointing to source. This feeds E03-05 lineage view automatically. |
| E05-08 | As a creator, I want to regenerate any individual derivative if I don't like the first draft so that I'm not stuck with a bad output and don't have to restart the whole job. | Must | 1 | Regenerate button per format card. Triggers targeted Claude call for that format only. Previous draft archived in JSONB array for reference. |
| E05-09 | As a creator, I want to repurpose a newsletter or blog post (not just video) by pasting in the text directly so that all my content formats can enter the repurpose workflow, not just video. | Should | 2 | Manual text input option alongside auto-import. Creates content_item with content_type=text_import, no platform. Feeds same Claude pipeline. |
| E05-10 | As a creator, I want to see the repurpose queue as a list of all in-progress and completed jobs with their status so that I always know what's awaiting review, what's scheduled, and what's been published. | Must | 1 | Queue page: list view. Columns: source title, formats selected, status (processing/review/approved/scheduled/published), created_at. Click to open job review view. |

| E06 EPIC | Scheduling & Publishing Schedule approved derivatives to publish at specific times, publish directly via platform APIs, and confirm delivery back into the system. Milestone: Phase 4 — Weeks 9–10 |
| --- | --- |

### Context

Scheduling is the final step of the repurpose workflow. An approved derivative can be published immediately or scheduled for a future time. Inngest cron jobs handle timed execution. Published content items feed back into the analytics pipeline automatically.

| ID | User Story | Priority | Points | Notes |
| --- | --- | --- | --- | --- |
| E06-01 | As a creator, I want to schedule an approved derivative to publish on a specific date and time so that I can batch-approve a week of content in one session and let Meridian handle timing. | Must | 3 | Date/time picker on approved derivative card. Write scheduled_at to repurpose_jobs. Inngest scheduled function fires at that time. Show in content calendar view. |
| E06-02 | As a developer, I want to build Inngest scheduled functions that publish derivatives to each platform via API at the scheduled time so that publishing is fully automated once a creator has approved and scheduled content. | Must | 5 | Per-platform publisher: Twitter API v2 (thread support), Instagram Graph API (caption post), LinkedIn API, Beehiiv API. Handle failures with retry + creator alert on repeated failure. |
| E06-03 | As a creator, I want to see a visual content calendar showing all scheduled and published content across platforms so that I can see my distribution plan at a glance and spot gaps. | Must | 2 | Monthly calendar grid. Each cell shows platform icon + content title for that day. Colour-coded by platform. Click to open derivative detail. |
| E06-04 | As a creator, I want to receive a notification (in-app and email) when a piece of content publishes successfully or fails so that I'm never left wondering if something went out. | Should | 1 | In-app: Supabase Realtime notification. Email: Resend transactional template. On failure: include retry option link. |
| E06-05 | As a creator, I want to see AI-suggested optimal publishing times for each platform based on my own historical engagement data so that I'm scheduling content when my specific audience is most active, not based on generic advice. | Should | 2 | Compute top 3 time windows per platform from performance_snapshots (filter to own data only). Surface as suggested time chips in the scheduler. Label: "Your audience is most active here." |
| E06-06 | As a creator, I want to cancel or reschedule a scheduled post before it publishes so that I can react to real-world events without losing the approved content. | Must | 1 | Cancel/Reschedule button on calendar items with scheduled status. Cancels Inngest job. Resets status to approved so it can be rescheduled. |

| E07 EPIC | Monetisation & Subscriptions Stripe billing, subscription tiers, feature gating, and the customer portal. Revenue infrastructure for launch. Milestone: Phase 4 — Weeks 10–11 |
| --- | --- |

### Context

Three tiers at launch: Free (1 platform, 5 repurpose jobs/month), Creator at $19/month (4 platforms, 30 jobs), Pro at $49/month (unlimited platforms and jobs, roster view up to 5 creators). All gating is server-side via Supabase RLS and API-route checks — never client-side only.

| ID | User Story | Priority | Points | Notes |
| --- | --- | --- | --- | --- |
| E07-01 | As a developer, I want to set up Stripe products and price IDs for Creator ($19/mo) and Pro ($49/mo) tiers, and connect Stripe webhooks to Supabase so that subscription state is always consistent between Stripe and the database. | Must | 2 | Stripe products: Meridian Creator, Meridian Pro. Webhook handler in Next.js API route. Events: checkout.session.completed, customer.subscription.updated, customer.subscription.deleted. Update creators.subscription_tier on each event. |
| E07-02 | As a creator, I want to upgrade my plan from the app via a hosted Stripe checkout page so that I can start my paid subscription without leaving the product. | Must | 2 | Stripe Checkout (hosted). Pre-fill email from Supabase Auth user. On success: Stripe redirects back to /dashboard?upgraded=true. Confetti moment. |
| E07-03 | As a creator, I want to manage my billing (update card, cancel, download invoices) via the Stripe Customer Portal so that I don't have to contact support for routine billing tasks. | Must | 1 | Stripe Billing Portal. One-click access from Settings > Billing. Return URL = /settings. |
| E07-04 | As a developer, I want to implement server-side feature gating for platform connection limits, repurpose job quotas, and roster size by subscription tier so that free users cannot access paid features through client manipulation. | Must | 2 | Gate checks in: Supabase RLS policies (connected_platforms count), API route middleware (repurpose_jobs monthly count), server component props. Never rely on client-side tier state alone. |
| E07-05 | As a free user, I want to see a clear upgrade prompt when I hit a tier limit (e.g., try to add a 2nd platform) so that I understand what I'm missing and how to unlock it with minimal friction. | Must | 1 | Modal: "You've reached your Free plan limit." Show what they get on Creator tier. One-click to Stripe Checkout. Do not block the whole app — only the specific gated action. |
| E07-06 | As a creator, I want to see a billing page showing my current plan, usage this month (repurpose jobs used / limit), and next billing date so that I have full visibility into what I'm paying for and how much I'm using. | Should | 1 | Settings > Billing. Query Stripe subscription for dates. Query repurpose_jobs for current month count. Simple summary card layout. |

| E08 EPIC | Mobile App (React Native / Expo) React Native mobile app sharing core logic with the web app via the monorepo. Key screens: dashboard, insights, repurpose queue, content calendar. Milestone: Phase 5 — Weeks 11–12 |
| --- | --- |

### Context

The mobile app is not a separate product — it is the web app's shared logic wrapped in a native shell. Because of the monorepo structure (packages/api, packages/types) and NativeWind for styling, most components are built once and adapted. Priority is given to the read/review flows (insights, queue review) since creation workflows are easier on desktop.

| ID | User Story | Priority | Points | Notes |
| --- | --- | --- | --- | --- |
| E08-01 | As a developer, I want to configure NativeWind so Tailwind utility classes work in the React Native app so that I write one styling system across web and mobile without context-switching. | Must | 1 | NativeWind v4 + Tailwind config shared from packages/ui. Test on iOS Simulator and Android Emulator before proceeding. |
| E08-02 | As a creator, I want to sign in to the mobile app with the same Google account I use on web so that my data is immediately available without re-onboarding. | Must | 2 | Supabase Auth on mobile via expo-auth-session. Same session as web — tokens synced via Supabase. Deep link back to app after OAuth. |
| E08-03 | As a creator, I want to see my analytics overview dashboard on mobile with the same key metrics as web so that I can check my content health from my phone without opening a laptop. | Must | 2 | Reuse packages/api query hooks. Adapt chart components: Recharts → Victory Native or react-native-gifted-charts. Scrollable card layout. |
| E08-04 | As a creator, I want to see my weekly pattern insights on mobile as swipeable insight cards so that I can review my insights during dead time (commute, etc.) without needing desktop. | Must | 2 | Horizontal swipe card stack. Each card: icon + headline + narrative + confidence. Dismiss gesture. Pull-to-refresh triggers insight refresh. |
| E08-05 | As a creator, I want to review and approve repurposed derivatives from my phone so that I can clear my review queue on mobile rather than waiting to get to a computer. | Should | 3 | Full repurpose job review flow on mobile. Tabbed format cards. Editable text areas. Approve / Reject / Regenerate actions. Same Supabase writes as web. |
| E08-06 | As a creator, I want to receive push notifications when a new pattern insight is available or a scheduled post publishes so that I'm pulled back into the app at moments of high value. | Should | 2 | expo-notifications + Expo Push Notification service. Trigger from Inngest job on pattern completion and on post publish. Notification taps deep-link to relevant screen. |

# Technical Guardrails for Claude/Cursor

The following conventions should be established in your CLAUDE.md / .cursor/rules file at the root of the repo. They prevent common AI-assisted coding errors and keep the codebase consistent across your build sessions.

## Code Conventions

- All TypeScript. No JavaScript files except config files that require it (next.config.js, tailwind.config.js).

- All database queries go through packages/api — never write Supabase client calls directly in component files.

- All environment variables are typed and validated at startup using a /lib/env.ts file with zod.parse().

- All Inngest functions live in packages/inngest and are imported into both web and edge function entrypoints.

- Never store OAuth tokens in localStorage or sessionStorage — only in Supabase via server-side session.

- All Claude API calls include a structured output schema in the prompt. Never let Claude free-form output that is parsed programmatically.

## Security Rules

- Feature gating always server-side. Never gate features using client-side subscription state alone.

- All API routes verify the Supabase session before any data operation.

- Stripe webhook handler validates the stripe-signature header on every request.

- OAuth tokens encrypted at rest — use Supabase Vault or pgcrypto for token columns.

## Branch and Commit Convention

- Branch names: feature/E[XX]-[short-slug], e.g., feature/E02-youtube-oauth

- Commit prefix matches epic: [E02] Add YouTube OAuth token refresh logic

- One GitHub Issue per user story. Issue title = story ID + story title.

- Never commit .env files. Use .env.example with all required keys listed but no values.

## Claude/Cursor Session Discipline

- Start each session by stating the user story ID and acceptance criteria in the first prompt.

- Ask Claude to write tests alongside implementation — not after.

- After completing each story, run the Supabase migration validator and Vercel build check before marking Done.

- Keep context windows tight: one story per session where possible. Paste only relevant files, not the whole codebase.

# Backlog Summary

| Code | Epic | Milestone | Stories | Est. Points |
| --- | --- | --- | --- | --- |
| E01 | Foundation & Auth | Weeks 1–2 | 6 | 14 pts |
| E02 | Platform Integrations | Weeks 2–4 | 8 | 22 pts |
| E03 | Analytics Engine | Weeks 3–5 | 9 | 24 pts |
| E04 | Pattern Intelligence | Weeks 5–6 | 7 | 18 pts |
| E05 | Repurpose Queue | Weeks 6–9 | 10 | 28 pts |
| E06 | Scheduling & Publishing | Weeks 9–10 | 6 | 16 pts |
| E07 | Monetisation & Subscriptions | Weeks 10–11 | 6 | 14 pts |
| E08 | Mobile App (React Native/Expo) | Weeks 11–12 | 5 | 12 pts |

Total: 57 user stories · 148 story points · 12-week MVP target

Must Have: 34 stories · 89 pts  Should Have: 17 stories · 46 pts  Could Have: 6 stories · 13 pts